## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-04-24
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-04-23 16:31 | MR2504/0648 | Continuous | 220KV_AMARKANTAK-SIDHI_Ckt_1 | 220KV_AMARKANTAK | NON-OCCM-MP | carry out the overhauling work of 220KV SF6 CB | 24-04-2025 07:00:00 | 26-04-2025 18:00:00 | Kripal Singh | 9425808924 | shall be given after normalisation of 220 KV GORABAZAR AMARKANTAK LINE
2 | 2025-04-23 12:06 | MR2504/0633 |  | 220KV_160MVA BBL X-MER | 220KV_ANUPPUR | NON-OCCM-MP | PRE-MANSOON MAINTENANCE & TESTING WORK | 24-04-2025 10:00:00 | 24-04-2025 18:00:00 | SK BHALAVI | 9425804704 | ok
3 | 2025-04-03 15:58 | MR2504/0090 | Continuous | 400KV_315 MVA X-MER NO.4 MAKE BHEL | 400KV_BHOPAL4 | NON-OCCM-MP | PRE-MONSOON MAINT & TESTING WORK | 23-04-2025 09:00:00 | 24-04-2025 18:00:00 | AKRAM KHAN | 9425804965 | Continuous
4 | 2025-04-11 12:39 | MR2504/0301 | Daily | 220KV_220 kV Bhopal-Mandideep line | 400KV_BHOPAL4 | OCCM-MP | Disc replacement work | 12-04-2025 09:00:00 | 25-04-2025 18:00:00 | Ankit Mehroliya | 9425804506 | ok, through sub ld
5 | 2025-04-18 12:27 | MR2504/0489 | Continuous | 220KV_220 KV Biba - Datia ckt. | 400KV_BINA4 | NON-OCCM-MP | Tower eretion for 576R | 21-04-2025 09:00:00 | 27-04-2025 17:00:00 | Er. Ranjeet Kumar | 9425805309 | Deffered
6 | 2025-04-18 12:21 | MR2504/0488 | Continuous | 220KV_220 KV Bina -Pichhore ckr. | 400KV_BINA4 | NON-OCCM-MP | Tower erection for 576R | 21-04-2025 09:00:00 | 27-04-2025 17:00:00 | Er. Ranjeet Kumar | 9425805309 | Deffered
7 | 2025-04-23 11:05 | MR2504/0630 |  | 220KV_220/132 KV, 160 MVA X-MER-II MAKE BBL | 220KV_CHANERA | NON-OCCM-MP | PREMANSOON MAINTENANCE WORK | 24-04-2025 10:00:00 | 24-04-2025 17:00:00 | SUKHRAM BADKHANE | 8462074203 | ok, through sub ld
8 | 2025-04-23 12:23 | MR2504/0636 | Daily | 132KV_132 kV Chhegaon - Bhikangaon DP Line | 132KV_CHHEGAON MAKHAN | OCCM-MP | Heavy Flash Over Disc Rep. & Broken Disc Rep. | 24-04-2025 06:00:00 | 25-04-2025 11:00:00 | C.H. Namdev | 9425802377 | sub ld
9 | 2025-04-17 15:37 | MR2504/0469 | Daily | 220KV_220 kV Chhegaon - Khandwa Ckt 2nd | 400KV_CHHEGAON4 | OCCM-MP | Hot Line Work for PID | 24-04-2025 10:00:00 | 03-05-2025 16:00:00 | C.H. Namdev | 9425802377 | not in WR list
10 | 2025-04-23 13:51 | MR2504/0638 |  | 40MVA_132/33KV_BBL_X'mer_2 | 220KV_CHHINDWARA | NON-OCCM-MP | PRE MANSOON MAINTENANCE WORK. | 24-04-2025 11:00:00 | 24-04-2025 18:00:00 | A.A.QURESHI | 9425804318 | ok
11 | 2025-04-23 16:14 | MR2504/0647 |  | 132KV_change over to Bus coupler of 132KV Garhakota Breaker | 220KV_DAMOH | NON-OCCM-MP | DPR Relay Testing work | 24-04-2025 14:00:00 | 24-04-2025 18:00:00 | M.K.Choubey | 9425801424 | ok, line to be in service through TBC
12 | 2025-04-23 16:11 | MR2504/0646 |  | 132KV_Change over to Bus coupler of 132KV Tejgarh Breaker | 220KV_DAMOH | NON-OCCM-MP | DPR Relay Testing work | 24-04-2025 10:00:00 | 24-04-2025 14:00:00 | M.K.Choubey | 9425801424 | ok, line to be in service through TBC
13 | 2025-03-24 20:17 | MR2503/0535 | Daily | 132KV_132kv deolond- beohari circuit | 132KV_DEVLOND | NON-OCCM-MP | OPGW string work | 25-03-2025 07:00:00 | 25-05-2025 19:00:00 | G.L. SAHU | 9425805102 | ok, line to be in service
14 | 2025-03-24 20:14 | MR2503/0534 | Daily | 132KV_132kv deolond- jhinna circuit | 132KV_DEVLOND | NON-OCCM-MP | OPGW string work | 25-03-2025 07:00:00 | 25-05-2025 19:00:00 | G.L. SAHU | 9425805102 | ok, line to be in service
15 | 2025-04-23 10:46 | MR2504/0629 |  | 220KV_220 KV GORABAZAR AMARKANTAK LINE | 220KV_GORABAZAR | NON-OCCM-MP | LEAKAGE ATTDEND OF R PHASE CVT | 24-04-2025 08:00:00 | 24-04-2025 11:00:00 | R.S BAIS | 9425163265 | ok, discom to be intimated, both 132kv ckts to be in service
16 | 2025-04-23 14:50 | MR2504/0642 |  | 220KV_100 MVA transformer-2 IMP Make | 220KV_GUJARKHEDI | NON-OCCM-MP | PRE MANSOON MAINTENANCE WORK | 24-04-2025 16:00:00 | 24-04-2025 20:00:00 | SUNIL PANWAR | 9425804939 | ok
17 | 2025-04-23 12:36 | MR2504/0637 |  | 220KV_160 mva x-mer ii nd MAKE-EMCO | 220KV_GUNA | NON-OCCM-MP | pre monsoon maintenance | 24-04-2025 10:00:00 | 24-04-2025 18:00:00 | M.S BHATNAGAR | 9425805096 | ok, through sub ld
18 | 2025-04-22 11:52 | MR2504/0588 | Continuous | 160MVA_220/132KV_BHEL_X'mer_1 | 220KV_HANDIYA | NON-OCCM-MP | Replacement of This X-Mer with New 200MVA X-Mer | 21-04-2025 10:00:00 | 30-06-2025 17:00:00 | J.D. Khoria | 9425804975 | Deffered
19 | 2025-04-15 19:57 | MR2504/0422 | Continuous | 400KV_400KV_UNIT#01 | 400KV_INDIRASAGAR | NON-OCCM-WR | ANNUAL MAINTENANCE | 16-04-2025 06:00:00 | 30-04-2025 18:00:00 | SHRI SANJAY PATEL | 9575074321 | as per system requirement
20 | 2025-04-05 15:03 | MR2504/0124 | Daily | 400KV_INDORE-NAGDA LINE | 400KV_INDORE4 | NON-OCCM-MP | REPLACEMENT OF DEFECTIVE DISC INSULATOR STRING | 17-04-2025 08:00:00 | 24-04-2025 18:00:00 | A.R. KANEL | 9425805217 | Deffered
21 | 2025-04-22 16:49 | MR2504/0628 |  | 400KV_400KV Indore - ISP-II line | 400KV_INDORE4 | NON-OCCM-MP | For erection of new gantry column for new 50MVAR r | 24-04-2025 08:00:00 | 24-04-2025 18:00:00 | Sandeep Umredkar | 9425820035 | ok, through sub ld
22 | 2025-04-23 13:56 | MR2504/0640 | Daily | 132KV_132 kV Jabalpur- Maneri Tap Gorabazar | 220KV_JABALPUR | NON-OCCM-MP | Tower Erection work of 43R, 46R. | 24-04-2025 07:00:00 | 28-04-2025 19:00:00 | Jitendra tiwari | 9425805298 | shall be given after normalisation of 220 KV GORABAZAR AMARKANTAK LINE
23 | 2025-04-23 13:56 | MR2504/0639 |  | 400KV_400KV MTPH((SSTPH)- Julwania line | 400KV_JULWANIYA4 | NON-OCCM-MP | For Jumper tightening & other line maintenance | 24-04-2025 10:00:00 | 24-04-2025 17:00:00 | Dinesh More | 9425806860 | ok, as opportunity s/d
24 | 2025-04-21 18:15 | MR2504/0582 | Continuous | 400KV_400 kV SSTPH-Julwaniya line | 400KV_JULWANIYA4 | NON-OCCM-MP | Lilo arrangement | 24-04-2025 07:00:00 | 25-04-2025 19:00:00 | M.K. More | 8817566466 | ok, through sub ld, approved only for 24th
25 | 2025-04-23 12:13 | MR2504/0634 |  | 132KV_50MVA Transformer No. 2 | 132KV_KATANGI | NON-OCCM-MP | Pre mansoon Maintenance work | 24-04-2025 09:00:00 | 24-04-2025 18:00:00 | Seema Dongre | 9425807247 | ok
26 | 2025-04-12 12:13 | MR2504/0320 | Continuous | 400KV_400KV KATNI DAMOH | 400KV_KATNI4 | NON-OCCM-MP | For Strenghtening Continues work . | 21-04-2025 09:00:00 | 26-04-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Continuous
27 | 2025-04-12 12:25 | MR2504/0321 | Continuous | 220KV_220KV KATNI DAMOH | 400KV_KATNI4 | NON-OCCM-MP | For Strenghtening Continues work . | 21-04-2025 09:00:00 | 26-04-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Continuous
28 | 2025-04-23 11:31 | MR2504/0631 |  | 132KV_132kv Nagda- khachrod ckt-1 line | 132KV_KHACHROD | NON-OCCM-MP | Disc insulator replacement work | 24-04-2025 09:00:00 | 24-04-2025 18:00:00 | Kamal solanki | 9425805262 | sub ld
29 | 2025-04-22 11:28 | MR2504/0586 |  | 132KV_132kV MANDLA-RTS LINE | 132KV_MANDLA | NON-OCCM-MP | Tightening Work of Sus Clamp & Emergency TC Work | 24-04-2025 11:00:00 | 24-04-2025 14:00:00 | S.K. BHALADHARE | 9425807264 | ok
30 | 2025-04-23 15:43 | MR2504/0644 |  | 132KV_132 Kv 40 MVA BBL-II | 132KV_MANGAWAN | NON-OCCM-MP | For RYB Phase CT Replacement | 24-04-2025 09:00:00 | 24-04-2025 18:00:00 | Mr. Kanisk Singh | 9425804656 | ok
31 | 2025-04-23 16:34 | MR2504/0649 |  | 220KV_220/132V 160 MVA BHEL X-MER NO-1 | 220KV_NARSINGHPUR | NON-OCCM-MP | Maintenance and testing work | 24-04-2025 17:00:00 | 24-04-2025 21:00:00 | Dinesh kushwaha | 9425801319 | ok
32 | 2025-04-13 21:55 | MR2504/0349 | Continuous | 220KV_Generating Unit No. 01 | 220KV_OMKARESHWAR | NON-OCCM-WR | Annual maintenance | 15-04-2025 10:00:00 | 29-04-2025 18:00:00 | Sh. Pankaj Sharma | 7898703187 | as per system requirement
33 | 2025-04-17 15:33 | MR2504/0468 | Daily | 220KV_220 kV Omkareshwar - Khandwa | 220KV_OMKARESHWAR | OCCM-MP | Hot LIne work for PID | 24-04-2025 10:00:00 | 03-05-2025 16:00:00 | C.H.Namdev | 9425802377 | not in WR list
34 | 2025-02-27 10:40 | MR2502/0431 | Continuous | 220KV_160MVA X-mer No I | 220KV_PANDHURNA | NON-OCCM-MP | Replacement. Of old 160MVA X Mer I CGL | 28-02-2025 09:00:00 | 27-05-2025 17:00:00 | MR Sahu | 9425804982 | Continuous
35 | 2025-04-20 12:05 | MR2504/0524 | Daily | 132KV_132 kV Pandhurna Multai | 220KV_PANDHURNA | NON-OCCM-MP | Old disc replacement work | 21-04-2025 08:00:00 | 26-04-2025 18:00:00 | A.M.Shende | 7587951136 | ok, through sub ld
36 | 2025-04-17 16:47 | MR2504/0471 | Continuous | 400KV_400 kv SSTPh Pithampur ckt -4 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Shutdown OPGW Stringing work | 22-04-2025 08:00:00 | 24-04-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered
37 | 2025-04-21 14:09 | MR2504/0567 |  | 315MVA_400/220KV_CGL_X'mer_1 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Pre monsoon maintenance work | 24-04-2025 10:00:00 | 24-04-2025 18:00:00 | Sh. Ankit Prajapati | 9425811370 | Deffered
38 | 2025-03-24 20:22 | MR2503/0536 | Daily | 132KV_132kv Rampurnakin- beohari circuit | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW string work | 25-03-2025 07:00:00 | 25-05-2025 19:00:00 | G.L.SAHU | 9425805102 | ok, line to be in service
39 | 2025-04-22 14:34 | MR2504/0615 |  | 132KV_132/33 KV 63 MVA BBL Transformer-III | 220KV_RATLAM | NON-OCCM-MP | Shutdown on 132KV Main Bus Section-II | 24-04-2025 11:00:00 | 24-04-2025 12:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
40 | 2025-04-22 14:45 | MR2504/0621 |  | 132KV_132KV Main Bus Section-II | 220KV_RATLAM | NON-OCCM-MP | Shutdown on 132KV Main Bus Section-II | 24-04-2025 11:00:00 | 24-04-2025 12:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
41 | 2025-04-22 14:31 | MR2504/0614 |  | 132KV_132 KV Inter-connector Feeder-II | 220KV_RATLAM | NON-OCCM-MP | Shutdown on 132KV Main Bus Section-II | 24-04-2025 11:00:00 | 24-04-2025 12:00:00 | NIKHIL DUNGE | 9472580148 | sub ld
42 | 2025-04-22 14:50 | MR2504/0622 | Continuous | 132KV_132 KV Interconnector-I will be transfer on 132 KV Bus-Coupler | 220KV_RATLAM | NON-OCCM-MP | Shutdown on 132KV Main Bus Section-II | 23-04-2025 09:45:00 | 24-04-2025 11:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
43 | 2025-04-22 14:37 | MR2504/0618 |  | 132KV_132/33 KV 40 MVA Transformer-II | 220KV_RATLAM | NON-OCCM-MP | Shutdown on 132KV Main Bus Section-II | 24-04-2025 11:00:00 | 24-04-2025 12:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
44 | 2025-04-22 14:36 | MR2504/0617 |  | 132KV_132/33 KV 50 MVA Transformer-I | 220KV_RATLAM | NON-OCCM-MP | Shutdown on 132KV Main Bus Section-II | 24-04-2025 11:00:00 | 24-04-2025 12:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
45 | 2025-04-22 14:39 | MR2504/0619 |  | 132KV_132 KV Incoming-III (BHEL 160 MVA) | 220KV_RATLAM | NON-OCCM-MP | Shutdown on 132KV Main Bus Section-II | 24-04-2025 11:00:00 | 24-04-2025 12:00:00 | NIKHIL DUNGE | 9425801487 | ok, through sub ld
46 | 2025-04-22 14:28 | MR2504/0612 |  | 132KV_132 KV Railway traction feeders-I | 220KV_RATLAM | NON-OCCM-MP | Shutdown on 132KV Main Bus Section-II | 24-04-2025 11:00:00 | 24-04-2025 12:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
47 | 2025-04-22 14:16 | MR2504/0609 | Continuous | 132KV_132 KV Ratlam-Jaora-II | 220KV_RATLAM | NON-OCCM-MP | Shutdown on 132KV Main Bus Section-II | 23-04-2025 09:45:00 | 24-04-2025 11:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
48 | 2025-04-22 14:29 | MR2504/0613 |  | 132KV_132 KV Railway traction feeders-II | 220KV_RATLAM | NON-OCCM-MP | Shutdown on 132KV Main Bus Section-II | 24-04-2025 11:00:00 | 24-04-2025 12:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
49 | 2025-03-07 14:50 | MR2503/0136 | Daily | 132KV_Shutdown (PTW) of 132 KV Rewa-Jhinna DCDS line | 220KV_REWA | NON-OCCM-WR | For installation of OPGW | 08-03-2025 07:00:00 | 30-05-2025 19:00:00 | Mr. Ajay Kumar Chaurasia | 9425805081 | ok, line to be in service
50 | 2025-03-07 14:53 | MR2503/0137 | Daily | 132KV_Shutdown (PTW) of 132 kv Rewa-Rampur Nakin DCDS line | 220KV_REWA | NON-OCCM-WR | For installation of OPGW | 08-03-2025 07:00:00 | 30-05-2025 19:00:00 | Mr. Ajay Kumar Chaurasia | 9425805081 | ok, line to be in service
51 | 2025-04-23 15:49 | MR2504/0645 |  | 132KV_Shutdown (H/T) of 132 KV Rewa-Mangawan Ckt-II DCDS line | 220KV_REWA | NON-OCCM-WR | Rectification of defects as per drone patrolling. | 24-04-2025 11:00:00 | 24-04-2025 17:00:00 | Mr. Ajay Kumar Chaurasia | 9425805081 | ok
52 | 2025-04-19 19:03 | MR2504/0522 | Continuous | 132KV_132kv Sabalgarh Sheopur Ckt IInd Tap to khandar | 220KV_SABALGARH | NON-OCCM-MP | Tower Errection & Stringing work | 21-04-2025 09:00:00 | 25-04-2025 17:00:00 | Suraj pawar | 942581 | Continuous
53 | 2025-04-23 16:39 | MR2504/0650 |  | 220KV_160 MVA Xmer Areva | 220KV_SATNA | NON-OCCM-MP | Pre mansoon testing work | 24-04-2025 09:00:00 | 24-04-2025 18:00:00 | Ravi Pandey | 9425805296 | ok
54 | 2025-02-04 18:10 | MR2502/0066 | Continuous | 400KV_400 KV ASHTA LINE- II | 400KV_SATPURA TPS | NON-OCCM-MP | WORK OF COMPLETE OVERHAULING & TESTING OF 400 KV B | 24-04-2025 09:00:00 | 26-04-2025 18:00:00 | Yashwant Warathe | 9425611046 | Deffered
55 | 2025-03-29 10:52 | MR2503/0660 | Daily | 132KV_132kV Seoni Nainpur SC | 132KV_SEONI1 | NON-OCCM-MP | Work for replacement of defective disc insulator | 01-04-2025 08:00:00 | 30-04-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
56 | 2025-04-09 16:05 | MR2504/0256 | Daily | 132KV_132KV Shahapura - Shrinagar line | 132KV_SHAHPURA | NON-OCCM-MP | 132 Kv Shahapura - Shrinagar link open from Shahap | 10-04-2025 10:00:00 | 30-04-2025 18:00:00 | H L Koshta | 7587951105 | ok
57 | 2025-04-19 19:06 | MR2504/0523 | Continuous | 132KV_132kv Sheopur Beerpur ADANI TBCB | 132KV_SHEOPUR KALAN | NON-OCCM-MP | Tower Errction & Stringing work | 21-04-2025 09:00:00 | 25-04-2025 17:00:00 | Suarj Pawar | 9425814079 | Continuous
58 | 2025-04-23 15:24 | MR2504/0643 |  | 220KV_220/33kv 50 mva bhel xmer no.2 | 220KV_SUKHA | NON-OCCM-MP | premonsoon maint and testing work | 24-04-2025 10:00:00 | 24-04-2025 17:00:00 | ashish sonkeshariya | 7587951153 | o&m consent required
59 | 2025-04-17 17:31 | MR2504/0478 | Daily | 132KV_132 kV Tikamgarh IC - 1st line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Installation work | 18-04-2025 07:00:00 | 19-06-2025 19:00:00 | MPPTCL Chhatarpur | 942580499 | ok, line to be in service
60 | 2025-04-17 17:34 | MR2504/0479 | Daily | 132KV_132 kV Tikamgarh-Badamalhera line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Installation work | 18-04-2025 07:00:00 | 19-06-2025 19:00:00 | Manoj Kumar Tiwari | 942580499 | ok, line to be in service
61 | 2025-04-16 13:31 | MR2504/0436 | Daily | 132KV_132 kV Tikamgarh-Badamalhera line & 132 kV Tikamgarh IC - 1st line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Installation Work | 17-04-2025 07:00:00 | 19-05-2025 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
62 |  | 241442 | Bay | NHPTL-TESTING-@-NHPTL - 400KV at BINA-NHPTL - 400KV |  | WRLDC | SC Test of 330MVA, 400/33-33kV, Power Transformer, 3 Phase. | 00:00 | 23:59 |  |  | ok
63 |  | 241796 | Line Circuits | 220KV-DAMOH-SAGAR-1 |  | WRLDC | AMP work of 220 KV Damoh-Sagar #1 line | 09:00 | 18:00 |  |  | ok
64 |  | 241740 | Line Circuits | 220KV-GWALIOR-GWALIOR-II-2 |  | WRLDC | FOR BAY MAINTENANCE & TESTING WORK | 08:00 | 18:00 |  |  | real time
65 |  | 241741 | Line Circuits | 220KV-ITARSI-BUDNI-2 |  | WRLDC | FOR BAY MAINTENANCE & TESTING WORK AT 220KV S/S BUDHNI | 08:00 | 18:00 |  |  | real time
66 |  | 244569 | Line Circuits | 220KV-ANNUPUR-KOTMIKALA-1 |  | WRLDC | for resagging work between loc 432-441 | 08:00 | 17:59 |  |  | real time
67 |  | 245562 | Line Circuits | 400KV-SINGAJI-PITHAMPUR-1 |  | WRLDC | for tower strengthening works | 08:00 | 17:59 |  |  | rescheduled from 25th
68 |  | 245562 | Line Circuits | 400KV-SINGAJI-PITHAMPUR-2 |  | WRLDC | for tower strengthening works | 08:00 | 17:59 |  |  | rescheduled from 25th